## Sheet1
RISK TABLE
RISK | CATEGORY | PROBABILITY | IMPACT | POINTER TO RMMM
1 = catastrophic impact
4 = negligible, low impact
Requirements aren't fully understood by the team. | Staff Size and Experience Risk | 5% probability | 1 | Mitigation: Make sure all members are properly guided.
Monitoring: Asses each members if they know already what to do.
Management: Conduct regular meetings.
Team doesn't have experience with the new technology to be implemented. | Staff Size and Experience Risk | 70% probability | 3 | Mitigation: Conduct bootcamps and seminars to equip the members with new knowledge.
Monitoring: Monitor the latest trend of the technology
Management: Provide members with manuals about the new technology
Team members aren't trained enough. | Staff Size and Experience Risk | 10% probability | 2 | Mitigation: Conduct bootcamps and seminars to equip the members with new knowledge
Monitoring: Monitor each members capabilities.
Management: Develop a skills development program for the members.
Inadequete team members to the the project. | Staff Size and Experience Risk | 15% probability | 3 | Mitigation:Efficient delegation of work based on each members skills and expertise
Monitoring: Monitor each members performance
Management: Hire more people.
No teamwork. | Staff Size and Experience Risk | 10%probability | 1 | Mitigation: Conduct peer reviews so that information about activity is shared.
Monitoring: Monitor the interpersonal relationship of each members
Management: Conduct a team building Activity
Resignation of a team member.(Are the unfinished works properly turned over?) | Staff Size and Experience Risk | 20% probability | 2 | Mitigation: Develop a continuity plan to avoid delays and for continues development of the project.
Monitoring: Monitor the current porogress of the work that will be left behind by the resigning employee.
Management: Make sure that the resigning employee have a replacement.
Software is too big for the team. | Risk Due to Project Size | 10% probability | 4 | Mitigation: Have an efficient delegation of work based on each members skills and expertise
Monitoring: Monitor the deadline.
Management: Plot a calendar of activity and set deadlines for each task.
Costs are more than what was budgeted. | Risk Due to Project Size | 15%probability | 3 | Mitigation: Careful planning of project.
Monitoring: Monitor the budget if its cost effective.
Management: Do a quanitative analysis if the project would be cost effective
Inaccurate/Insufficient data given by the Client( e.g. Formulas for the Finance/Accounting System) | Risk due to the Customer | 10%probability | 1 | Mitigation: Make sure that the customer provided accurate information
Monitoring: Monitor if the datas given are complete.
Management: Continuous coordination with the client.
Clients requirements for the program are too vague. | Risk due to the Customer | 30%probability | 1 | Mitigation: Clarify any vague information given by the clients.
Monitoring: Have a representative of the client to monitor the progress of the project.
Management: Conduct regular meetings with the client for clarifications about the project.
The progam is too complex to use for the End Users. | Risk Due to Business Impact | 30% probability | 4 | Mitigation: Make a user-friendly program
Monitoring: Monitoring the program if it's becoming too complex.
Management: Conduct Research on what would be better for the end users.
Calamities, Power Outage, Internet Connection Down,System Down. | Fortuotious Events | 10% probability | 3 | Mitigation: Always have a contingency plan when fortuitious events happen.
Monitoring: Make sure all files have a back up.
Management: Develop an emergency Plan.
Lack of tools to be used to build the product. | Technology Risk | 20% probability | 3 | Mitigation: Invest for the proper tools and softwares to be used.
Monitoring: Monitor the latest trend in tehnology.
Management: Provide the members with the right tools for a specific project.